## Essence Card Progression
Team Members | Responsibility_1 | Responsibility_2 | Responsibility_3 | Responsibility_4 | Remarks
Advaith Moholkar | MinIO Storage | Apache Polaris | Apache Iceberg | Trino | Engineer 2: Streaming & Quality
Debjit Ghorai | FastMCP Server | sqlglot | LLM Agent | Experimentation | Engineer 4: AI & Security
Adithya Subhash | Redpanda Broker | Apache Flink | Flink SQL | Data Quality | Engineer 3: Storage & Catalog
Aditya Jain | PostgreSQL | Python Data Gen | Debezium Server | CDC Streaming | Engineer 1: Source & CDC
Alphas | Manager | Card_No. | Start_Date | Completion_Date | Remarks
Opportunity | Aditya Jain | 1/6 Identified | 2026-08-12 | 2026-08-14 | Idea behind opportunity identified.
Stakeholder | Adithya Subhash | 1/6 Recognized | 2026-08-12 | 2026-08-14 | Key stakeholder groups represented.
Requirements | Advaith Moholkar | 1/6 Conceived | 2026-08-12 | 2026-08-15 | Opportunity clear.
Software Systems | Debjit Ghorai | 1/6 Architecture Selected | 2026-08-12 | 2026-08-25 | Technologies selected.
Team | Aditya Jain | 1/6 Initiated | 2026-08-12 | 2026-08-14 | Required result clear.
Way of Working | Adithya Subhash | 1/6 Principles Established | 2026-08-12 | 2026-08-15 | Key practices & tools selected.
Team | Advaith Moholkar | 1/5 Seeded | 2026-08-12 | 2026-08-14 | Required competencies identified.

## Requirements
Project_Title | Project_Start_Date | Project_End_Date | Lead | Remarks
Enterprise Agentic Streaming Lakehouse | 2026-08-12 | 2026-10-25 |  | 10 weeks is tentative :)
Functional Requirements (FR) -- What the system is expected to do -- Prioritize; Risk analysis
Reference Code | Functional Requirement (FR) | Features, edge cases, considerations, assumptions, etc. | Priority | Risk
FR_1 | Real-time Change Data Capture (CDC) | Features: Read PostgreSQL WAL; publish JSON to Redpanda. Edge Case: Handling schema changes in source DB. | High | Medium
FR_2 | Stateful Stream Processing | Features: Filter, clean, and deduplicate streams. Edge Case: Handling late-arriving events or out-of-order data. | High | High
FR_3 | Lakehouse Storage | Features: Write processed streams to open-table format (Iceberg) on object storage (MinIO). Assumption: Local Docker volume persistence. | High | Medium
FR_4 | Distributed Analytical Querying | Features: Execute complex SQL aggregations over Lakehouse. Edge Case: Optimizing query performance without indexing. | High | Low
FR_5 | Agentic AI Interface (MCP) | Features: Translate natural language to Trino SQL via LLM. Security: Must block INSERT, UPDATE, DROP, or hallucinated tables. | Medium | High
Non-functional Requirements (NFR) -- How the system is expected to perform - Prioritize; Risk analysis
Reference Code | Non-Functional Requirement (NFR) | Features, edge cases, considerations, assumptions, etc. | Priority | Risk
NFR_1 | Fault Tolerance & Recovery | Features: The system must survive container crashes. Flink must use checkpointing for exactly-once processing. Redpanda must retain durable offsets. | High | High
NFR_2 | Resource Efficiency | Constraint: The entire distributed stack must execute reliably on a single developer machine (e.g., 16GB RAM, 8-Core CPU) using Docker Compose without out-of-memory (OOM) crashes. | High | Medium
NFR_3 | Data Consistency (ACID) | Features: Trino queries must never return dirty, incomplete, or corrupted data while Flink is actively writing to the Iceberg tables. | High | Low
NFR_4 | Security & Isolation | Constraint: The Model Context Protocol (MCP) server must operate via a strictly scoped, read-only database user. It must be physically impossible for the LLM to execute DROP, ALTER, or INSERT commands. | High | High
NFR_5 | End-to-End Latency | Performance: The time taken from a record mutating in PostgreSQL to being queryable in Apache Iceberg should not exceed 5 seconds under normal local load. | Medium | Medium

## Traceability Matrix
Requirements | Priority | Risk | Remarks
FR_1 (Real-time CDC)
Module 1: Postgres & Data Gen | High | Medium | Set up transactional operational DB and write Python faker script.
Module 2: Debezium Server CDC | High | Medium | Configure standalone Quarkus app to capture Postgres WAL logs.
Module 3: Redpanda Broker | High | Medium | Deploy C++ Raft broker and connect the Debezium source stream.
FR_2 (Stream Processing)
Module 4: Flink Stream Processing | High | High | Implement declarative Flink SQL for quality validation and DLQ routing.
FR_3 (Lakehouse Storage)
Module 5: Object Storage & Iceberg | High | Medium | Establish MinIO buckets and configure Flink exactly-once commits.
Module 6: Polaris Catalog & Trino | High | Medium | Set up REST metadata catalog and distributed query compute engine.
FR_4 (Analytical Querying)
Module 7: FastMCP Server init | Medium | High | Expose the get_schema_context tool via retrieval-augmented generation.
FR_5 (Agentic AI Interface)
Module 8: LLM Integration | Medium | High | Formulate prompts and execute analytic queries via LLM API endpoint.
Module 9: sqlglot AST Guardrails | High | High | Computationally block mutation and DDL queries via AST traversal.
Module 10: Experimentation & Teardown | Medium | Low | Compare LLM vs Non-LLM systems and record exact latency/accuracy metrics.
NFR_1 (Fault Tolerance)
Module_1 (Ingestion Layer) | High | Medium | Kafka broker durability and durable offsets.
Module_2 (Processing Layer) | High | High | Flink state backend and checkpointing.
NFR_2 (Resource Efficiency)
Module_1 (Ingestion Layer) | High | Low | Kafka/Debezium strict JVM memory limits.
Module_2 (Processing Layer) | High | Medium | Flink TaskManager slot allocation.
Module_3 (Storage Layer) | High | Low | MinIO storage volume persistence limits.
Module_4 (Query Layer) | High | Medium | Trino worker memory constraints.
Module_5 (Serving Layer) | High | Low | MCP server local execution overhead.
NFR_3 (Data Consistency)
Module_3 (Storage Layer) | High | Low | Iceberg optimistic concurrency control.
Module_4 (Query Layer) | High | Low | Trino read isolation levels.
NFR_4 (Security)
Module_4 (Query Layer) | High | Medium | Trino user roles and read-only permissions.
Module_5 (Serving Layer) | High | High | MCP strict SQL injection guardrails.
NFR_5 (End-to-End Latency)
Module_1 (Ingestion Layer) | Medium | Low | Debezium polling intervals.
Module_2 (Processing Layer) | Medium | Medium | Flink windowing and watermark delays.
Module_3 (Storage Layer) | Medium | Low | Iceberg commit frequency.
Module_4 (Query Layer) | Medium | Low | Trino query execution planning time.
Dependency analysis between FR and NFR
FR/NFR | NFR_1 | NFR_2 | NFR_3 | NFR_4 | NFR_5 | Remarks
FR_1 | Finish - Finish | Start - Start | Finish - Start | None | Start - Start | Fault tolerance is built into CDC (FF); memory limits apply from day one (SS); consistency validated after CDC completes (FS); latency tracking begins immediately (SS).
FR_2 | Finish - Finish | Start - Start | Finish - Finish | None | Start - Start | Flink checkpointing and fault tolerance are coupled at completion (FF); resource limits enforced from start (SS); exactly-once guarantees verified together (FF); windowing latency is inherent (SS).
FR_3 | Start - Start | Start - Start | Finish - Finish | Start - Start | None | Replication configured from start (SS); volume limits set from start (SS); ACID concurrency validated at completion (FF); bucket IAM policies from start (SS); storage latency is negligible.
FR_4 | None | Start - Start | Finish - Start | Finish - Finish | Start - Start | Queries are stateless and retriable; memory bounding from start (SS); storage must be consistent before querying (FS); read-only roles enforced by go-live (FF); query optimization is inherent (SS).
FR_5 | None | None | None | Finish - Finish | Start - Start | Minimal fault tolerance needed; inference is outsourced; agent does not mutate data; AST guardrails must be fully locked before agent goes live (FF); token generation latency is inherent (SS).

## Budget & Purchase
Particulars | Cost per unit | Nos. | Year / Month | Year / Month | Year / Month | Remarks
Manpower
Recurring
Non-recurring
Contingency
Overhead
Total
Particulars | Vendor | Nos. | Purchase_Date | Cost | GST | Remarks
Details of purchases are recorded

## Sprint Plans
Project_Title | Project_Start_Date | Project_End_Date | Lead | Date | Progress (%) | Remarks
Enterprise Agentic Streaming Lakehouse | 2026-08-12 | 2026-10-25 |  |  |  | 10 weeks is tentative :)
Sprint_No. | Sprint_Start_Date | Sprint_End_Date | Tentative Deliverables | Module_Start | Module_End | Status | Responsible | Priority | Remarks
1 | 2026-08-12 | 2026-08-25 | Module 1: Postgres & Data Gen | 2026-08-12 | 2026-08-18 | Deployed | Aditya Jain | High | Set up transactional operational DB and write Python faker script.
|  |  | Module 2: Debezium Server CDC | 2026-08-19 | 2026-08-25 | Deployed | Aditya Jain | High | Configure standalone Quarkus app to capture Postgres WAL logs.
2 | 2026-08-26 | 2026-09-08 | Module 3: Redpanda Broker | 2026-08-26 | 2026-09-01 | Coding | Advaith Moholkar | High | Deploy C++ Raft broker and connect the Debezium source stream.
|  |  | Module 4: Flink Stream Processing | 2026-09-02 | 2026-09-08 | Planning | Advaith Moholkar | High | Implement declarative Flink SQL for quality validation and DLQ routing.
3 | 2026-09-09 | 2026-09-22 | Module 5: Object Storage & Iceberg | 2026-09-09 | 2026-09-15 | Not started | Adithya Subhash | High | Establish MinIO buckets and configure Flink exactly-once commits.
|  |  | Module 6: Polaris Catalog & Trino | 2026-09-16 | 2026-09-22 | Not started | Adithya Subhash | High | Set up REST metadata catalog and distributed query compute engine.
4 | 2026-09-23 | 2026-10-06 | Module 7: FastMCP Server init | 2026-09-23 | 2026-09-29 | Not started | Debjit Ghorai | High | Expose the get_schema_context tool via retrieval-augmented generation.
|  |  | Module 8: LLM Integration | 2026-09-30 | 2026-10-06 | Not started | Debjit Ghorai | High | Formulate prompts and execute analytic queries via LLM API endpoint.
5 | 2026-10-07 | 2026-10-20 | Module 9: sqlglot AST Guardrails | 2026-10-07 | 2026-10-13 | Not started | Debjit Ghorai | High | Computationally block mutation and DDL queries via AST traversal.
|  |  | Module 10: Experimentation & Teardown | 2026-10-14 | 2026-10-20 | Not started | Full Team | Medium | Compare LLM vs Non-LLM systems and record exact latency/accuracy metrics.

## Test Sheet
Module | Function | Start_Date | End_Date | Status | Test_Id / Ticket_Id | Date | Status | Team_Member | Remarks
Module_1 | Function_1
Function_2
Module_2 | Function_3
Function_4